## User stories
| Main User Story | Sub-Task
1 | Authentication / Login Module | Signup for customer and admin
Login
Logout

## Ranjith Backend
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Login Module
1.1 | Signup
1.1.1 | Signup for customer
1.1.1.1 | Test cases | 1 |  | Tuesday
1.1.1.2 | Backend Logic code | 1 |  | Tuesday
1.1.1.3 | Validations + Exception Handling+Messages from backend | 1 |  | Tuesday
1.1.2 | Signup for Admin
1.1.2.1 | Test cases | 1 |  | Tuesday
1.1.2.2 | Backend Logic code | 1 |  | Wednesday
1.1.2.3 | Validations + Exception Handling+Messages from backend | 1 |  | Wednesday
1.2 | Login
1.2.1 | Test cases | 1.5 |  | Wednesday
1.2.2 | Backend Logic code with encryption and decryption | 2 |  | Wednesday
1.2.3 | Validations + Exception Handling+Messages from backend | 1 |  | Thursday
1.3 | Logout
1.3.1 | Backend Logic code | 1 |  | Thursday
1.3.2 | Messages from Backend | 1 |  | Thursday
1.4 | Overall Review | 0.5 |  | Thursday